Board Meeting

December 11 @ 12:00p.m

7000 Archer Road Justice, IL 60458

Teleconference Line 978-990-5007, Enter access code 718309.

MEETING MINUTES

Commission Chairman Mary Jane Mannella called the Meeting of December 11, 2025, to order at 12:01pm

Roll Call

| COMMISSIONERS mary jane mannella GEORGE PASTORINO john Zapala |  | 7000 sOUTH aRCHER rOAD jUSTICE, IL 60458-1196 PHONE: 708-458-7010 WWW.JWSWC.ORG |
| --- | --- | --- |

Public Comment

Motion by: Mannella to open the floor for public comment.

Second by: Pastorino

Roll Call Vote: 3/0

Motion by: Mannella to close the floor for public comment.

Second by: Pastorino

Roll Call Vote: 3/0

Minutes

Approval of board meeting minutes on October 23, 2025

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

Financial

- Paid Invoices from October 22, 2025 – December 9, 2026, $1,455,760.24

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

- Almost 2 months

- Geradi was paid off

- Mauro for East Ravine

- Final Payment to tollway for the IGA

- Cash in Banks, All Accounts October and November 2025

- Audit Update

- Discussion and Approval of 2025 General Fund Budget

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

- Discussion and Approval of 2025 Capital Improvement Budget

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

- Collections Justice and Willow Springs

Commissioner Report

- Letter from the Village of Willow Springs requesting a registration fee for their annual tree trim.

Donation $100.00

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

- Letter from the Village of Justice requesting a donation for their Holiday Program/Scholarship Program.

Donation $1500.00

Motion by: Pastorino

Second by: Mannella

Roll Call Vote: 3/0

- Approval of regular board meeting dates for 2026

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

- Approval of Holiday Schedule for 2026

Motion by: Mannella

Second by: Pastorino

Roll Call Vote: 3/0

- Christmas bonuses for all employees in the amount of $400.00

Motion by: Manella

Second by: Pastorino

Roll Call Vote: 3/0

Engineer’s Report

- Approval of releasing retainer/final payment to Gerardi Sewer and Company for the 79th Court Project in the amount of $69,986.50.

Motion by: Pastorino

Second by: Mannella

Roll Call Vote: 3/0

- Retainer payout, project is completed

- Contract is closed

- Approval of final payment (minus retainer) to Mauro Sewer Construction for East Ravine in the amount of $281,854.63

Motion by: Zapala

Second by: Pastorino

Roll Call Vote: 3/0

- Construction is completed

- Minus retainer

- At Budget, a little under to be exact.

- Archer Avenue IDOT storm sewer conflict with JWSWC 24" main status update.

- IDOT storm sewer collapsed and found our water main runs over the top of the manhole

- Abandoned a manhole and the lid collapsed blocked the sewer.

- Tentative deal shutting down the 24inch, depressing the water line and cleaning out the debris

- IDOT will restore the inlet

- Long term budget IDOT will reconstruct the issue, will build a new on the opposite side of the road – 7 years down the road

- Headquarters Architectural Concept Plan status update.

- Potential concepts - either rebuild or turn down

- Village of Justice 75th Street project status update: Dispute regarding cost assignments for storm sewer replacements

- Bid opening everything was above what was projected

- Attempted to fix it but the cost was put on the Water Commission

- Letter was written to the Village requesting a meeting at their water main is not the water commissions issue

- Analysis of prior projects and the bid show the cost is ballooned as far as the water Commission

- 79th Street 20 inch is completed; Unique will provide pay request next month’s meeting

- Annual water audit is in the works, 9.6% now but we must go over Burr Ridge share will have to be looked at.

Legal

- Update on Chief Trailer Park

- Engineer report received deficiency in fire suppression system

- JWSWC disagrees with it

- Engineer was misinformed on the goal with the park

- Requesting meeting with the Village

Executive Directors Report

- Liability and health insurance renewal

- Premium increases

- Village of Willow Springs Winter Fest

- Tree was decorated and great fireworks

- Village of Justice Winter Wonderland

- Chicago water partner advisory council (CWPAL) – cost of service study

- Executive board was formed from suburbs who receive water from the City of Chicago

- Cost of service allocation based on AWWA (American Water works Association) determines a new rate to wholesalers

- Rates will be determined how much water main from the City of Chiago to the water meter owned by the suburb

- Formula has been created to put in the numbers and get the answer

- In this formula it will have pension liability, admin, unfunded liability, pension and amount of unmetered water on the City of Chicago side.

- Some of Chicago properties are unmetered and they want to put that on the suburbs

- Requested 5 years look back and what percentage of the project was completed in the City of Chicago.

- Next meeting will go over these points.

- Meeting with the Village of Bedford Park – CWPAL

- Suggested the City of Chicago still has to be paid, Independence of JWSWC is top priority.

- JWSWS can purchase Minimum water from Chicago and purchase the rest of water from Bedford if their cost is lower

- Still in preliminary stages.

- Update on Cook County Project

- 79th and 86th Avenue small excavation

- Water main was exposed and left exposed

- The main split – a clamp would be placed

- We inquired about the cost for 3 months due to Cook County leaving the main exposed

- JWSWC was provided with a claim form to fill out

Operator – Field Report

- Update on Water Main Breaks

- 17 water main breaks, most on 6-inch water main, residential areas

- 2 on 12-inch water main

- No complications, the water main was fixed without incidents

- Hodgkins’s emergency inter-connect update

- Project is completed

- A few new water mains, new valves, new hydrants – JWSWC benefited – interconnect is not one that is used often but, will be there if needed.

Customer/Community Matters

- Appeal Letter from Dolores Trachitella, 117 Santa Fe requesting a reduction on her water bill.

Reduction Amount: $209.60

Motion by: Mannella

Second by: Zapala

Roll Call Vote: 3/0

Personnel

- Acceptance of employees’ FMLA request

Motion by: Mannella

Second by: Pastorino

Roll Call Vote:  3/0

Old Business

- Present any Old Business

New Business

- Present / Consider any New Business

Closed Session

A Closed Session, as permitted by 5 ILCS 120/2, will be held to discuss and consider the appointment, compensation, discipline, performance, or dismissal of specific employees of and / or to the Commission.

Motion by: __________ that the Commission suspends the regular meeting and enters a closed session to discuss and consider the appointment, compensation, discipline, performance, or dismissal of specific employees of and / or to the Commission.

Motion by: Mannella that all Correspondence and Documents received by and / or presented to the Commission for this meeting be received, accepted, and filed as noted.

Second by: Pastorino

Roll Call Vote: 3/0

Motion by: Pastorino that the Commission adjourns the Board Meeting of December 11, 2025 at 12:48pm

Second by: Mannella

Roll Call Vote: 3/0